**PROJECT UPDATE**

DECEMBER 2017

Project title - East Midlands Gateway Project duration - 140 Weeks Current Week No. 48

**INTRODUCTION**

The project, East Midlands Gateway, aims to

create 7,000 new jobs and provide new rail and

road connected distribution and storage facilities

including:

. An intermodal freight terminal

. Up to 557,414 m2 (6m sq ft) of rail served warehousing and ancillary service buildings;

. A new rail line connecting the terminal to the

Castle Donington branch freight only line;

. New road infrastructure and improvements to the existing road infrastructure;

. Strategic landscaping and the creation of new publicly accessible open areas;

. Bus interchange.

. New dedicated Bypass for Kegworth giving direct access to the A453 and the M1

**CURRENT ACTIVITIES**

Earthworks – reduced output due to winter weather as anticipated.

A453 Junction has been completed.

J24 roundabouts improvement works have started with the East side of the junction aiming to be complete April 2018

J24a –J24 improvement works are progressing. Working in conjunction with Smart Motorways we are building a new on & off slip road to Junction 24

**PLANNED ACTIVITIES:**

Onsite earthworks will continue for the next 24 months

Junction 24a – J24 improvement works are progressing. Road construction is well progressed.

Main Street Lockington works will commence in January 2018 to construct new access to the village.

Works will commence to remove Warren Lane roundabout early 2018

Junction 24 improvement East side of the M1 surfacing anticipated to be carried out Spring 2018

.

**FURTHER PROJECT INFORMATION**

There are several ways of finding out further information, if you wish to be included in the project updates please contact the construction team.

. East Midlands Gateway web page [www.eastmidlandsgateway.co.uk](http://www.eastmidlandsgateway.co.uk/)

. Highways England Web page [www.gov.uk/government/organisations/highways-england](http://www.gov.uk/government/organisations/highways-england)

. Contact your parish council.

. Contact the construction team

**TRAFFIC INFORMATION**

Current and planned traffic sequencing can be found on the scheme web page:-

[www.trafficengland.com](http://www.trafficengland.com/) or [www.roadworks.org](http://www.roadworks.org/)

**CONTACTS**

If you wish to contact the development construction team directly either:

**E-mail:-** [**emg-enquiries@winvic.co.uk**](mailto:emg-enquiries@winvic.co.uk)

**Tel:- 07514 227 681**

**PROJECT UPDATES**

Regular newsletters will be distributed to key stakeholders including local authorities, parish councils and local businesses by email. They will also be available on the East Midlands Gateway web page however if you wish to be copied in please send an e-mail to:-

[emg-enquires@winvic.co.uk](mailto:emg-enquires@winvic.co.uk)

We will then add you to the distribution list for the newsletter

**PROJECT MANAGER’S COMMENT**

As the Project Manager for the East Midlands Gateway, I will ensure that during the construction phase we will work closely with local communities and key stakeholders to minimize disruption. So please feel free to contact my construction team with any concerns.



Yours Faithfully,

**Mark Skelton**

**EMG Project Manager.**

The Winvic Way

**RESPECT** Respect for all of our colleagues, regardless of their position in the organisation. Respect for suppliers, communities, the environment – and for our customers. By valuing the opinions and concerns of others our solutions deliver the best outcome for all stakeholders.

**LOYALTY** To customers, each other, and our suppliers.

**HONESTY** Allows us to tackle difficult conversations.

Straight-talking generates trust and helps to solves problems quickly. We keep clients in the picture

at all times, so there will be no nasty surprises on cost or delivery.

**CHALLENGING/QUESTIONING** Always asking ourselves if there is a better way.

The commitment to continuous improvement underpins our position as industry leaders.

**PASSION: PRIDE, TENACITY, DRIVE** The winning mentality. If it’s in our hearts it’s at the heart of the business. The most important ingredient in the recipe for success.



If you would like to forward your input on any aspects of our newsletter or construction activities, please use the space provided and return to: Winvic Construction Ltd, Brampton House, 19 Tenter Road, Moulton Park Industrial Estate, Northampton, NN3 6PZ.

T +44 (0)1604 678960 E [mail@winvic.co.uk](mailto:mail@winvic.co.uk) winvic.co.uk



