CASTLE DONINGTON WAKES - RISK ASSESSMENT

| Date of Event |  | 26-29 October 2022 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment completed by: |  |  |  | Castle Donington Parish Council Office |  |  |  |  |  |  |  |  |  |  | Date |  | 4/08/22 |  |  |  |  |
| Assessment checked by: (Risk Assessor) |  |  |  |  |  | Jayne Wintle / Fiona Palmer |  |  |  |  |  |  |  |  | Date |  | 4/08/22 |  |  |  |  |
| Special groups of persons considered |  |  |  |  | Police/ Fire/ Ambulance Officers, Members of Public, Showmen & Event key personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ALL INCIDENTS TO BE REPORTED TO EVENT CONTROL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WORK ACTIVITY |  |  | HAZARD |  |  |  | H/M/L | LIKELIHOOD |  |  |  |  | H/M/L | RISK |  | FURTHER ACTION REQUIRED |  |  |  |  |  |
| No. | Description of task |  | (Including description of potential severity |  |  |  |  | Groups exposed & evidence of previous harm |  | Existing controls in place? |  |  |  | H/M/L |  | ACTION - Person responsible, date for achievement |  |  | Review action & date |  |  |
| 1 | Cables |  | Slips, trips, falls Potential for severe injury |  |  |  | H 3 | All groups* - one previous incident (1999), person tripped over cable, leg injuries |  | All cabling covered by rubber ramping & boxing Event Marshal to check on security of rampings and boxings and to be recorded. |  |  | L 1 | L 3 |  | CD First Responders to provide First Aid during the main event and XXX (First Aider) on set-up day |  |  |  |  |  |
| 2 | Road signs |  | Slips, trips, falls. Potential for severe injury |  |  |  | H 3 | All groups* - previous incident 2012 |  | All signs to be sand bagged Event Marshal to check and record security of signs and sandbags. |  |  | M 2 | M 2 |  | CD First Responders to provide First Aid during the main event and XXX (First Aider) on set-up day |  |  |  |  |  |
| 3 | Generators & exhaust fumes |  | Noise, inhalation of fumes from generators & other engines. Burning. Potential for severe harm |  |  |  | H 3 | All groups* - no previous evidence |  | Noise measurement & monitoring by District Council & Event Marshal. All engines and generators shielded / contained Event Marshal to check on coverings, isolations. |  |  | L 1 | L 3 |  | CD First Responders to provide First Aid during the main event and XXX (First Aider) on set-up day NWLDC Environmental Health advised of event |  |  |  |  |  |

| WORK ACTIVITY |  | HAZARD | H/M/L | LIKELIHOOD |  | H/M/L | RISK | FURTHER ACTION REQUIRED |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Description of task | (including description of potential severity |  | Groups exposed & evidence of previous harm | Existing controls in place? |  | H/M/L | ACTION - Person responsible, date for achievement | Review action & date |
| 4 | Ride collapse / breakdown | Impact from moving equipment, including emergency vehicles. Potential for severe harm | H 3 | All groups* - one previous incident (2001). Showman injured whilst erecting fair: hospitalised | All stalls, etc tested by relevant bodies prior to arrival, H & S documentation provided. Mobile communication in use between Event Marshal, Police, Event stewards, Community First Responders XXX (First Aider) | L 1 | L 3 | Event Marshal to carry out visual check of site. All documents to be provided and approved prior to ride arrival. Community First Responders to provide First Aid during the main event and G Thomas (First Aider) on set-up day. Emergency Services requested to check access/egress routes |  |
| 5 | Canopy (& heights) | Impact from collapsing equipment, height restrictions. Potential for serious injury | H 3 | All groups* - no previous incident | All canopy edges checked for clear illumination & light clearance. Event Marshal to check on canopy visibility | L 1 | L 3 | Community First Responders to provide First Aid during the main event and XXX (First Aider) on set-up day |  |
| 6 | Wagon parking/ vehicle movement | Access/egress for public, showmen, Emergency Services (footpaths & roadways), collision, injury to public. | M 2 | All groups* - previous parking incidents from local residents/workers, showmen | Published information pre-Wakes, Road Traffic Orders in place to control vehicle parking/ movement; signs, cones, road closures, diversions in place. Parking identification issued to Showmen | L 1 | L 2 | Event Marshal to check parked vehicles and contact police if obstruction caused. |  |
| 7 | Traffic movement / deliveries | Injuries to public or ride operator | L 3 | All groups* - no previous incident | Temporary Traffic Road Orders in place, monitored by Event stewards in place; signage & traffic barriers sited. | L 2 | L 2 | Community First Responders to provide First Aid during the main event and XXX (First Aider) on set-up day |  |

| WORK ACTIVITY |  | HAZARD | H/M/L | LIKELIHOOD |  | H/M/L | RISK | FURTHER ACTION REQUIRED |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Description of task | (Including description of potential severity |  | Groups exposed & evidence of previous harm | Existing controls in place? |  | H/M/L | ACTION - Person responsible, date for achievement | Review action & date |
| 8 | Crowd control / pinch points | Crushing due to crowd congestion & pinch points. Potential for serious injury | H 3 | All groups* - no previous incident | Event Marshal & stewards to monitor crowds, potential bottlenecks, etc, to liaise with Emergency Services & Showmen – mobile communications In place Contingency Plan issued pre-event with appropriate mobile phone numbers including Emergency contacts. Sufficient Steward / Police cover as in previous years | L 1 | L 3 | Event Marshal and stewards to liaise individually with Showmen; Contingency Plan issued pre-event with appropriate mobile phone numbers including Emergency contacts. Sufficient Police / Steward cover as in previous years |  |
| 9 | Emergency evacuation/ Services | Ingress / egress from zones, public interference, crushing, trampling | M 2 | All groups* - no previous incident | Published Contingency Plan pre-Wakes – Appx A. Spacing of rides to allow access for emergency vehicles. Mobile communications in place | L 1 | L 2 | Event Marshal to liaise with stewards & Emergency Services as per Contingency Plan; also to check on access/egress to site |  |
| 10 | Noise | Damage to hearing. Potential for severe harm. | M 2 | All groups* - no previous incident | Noise monitoring by Event Marshals | L 1 | L 2 | NWLDC advised of event and advised of any issues |  |
| 11 | Sight | Damage to sight from lights, potential fits for epileptics from strobe and ultra violet lights. Potential for serious harm | H 3 | All groups* - no previous incident | All H&S regs complied with by Showmen | L 1 | L 3 | Event Marshal to check on H&S compliance & maintain contact with appropriate Emergency Services Showmen to shut off lights in event of epileptic incident |  |

| WORK ACTIVITY |  | HAZARD | H/M/L | LIKELIHOOD |  | H/M/L | RISK | FURTHER ACTION REQUIRED |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Description of task | (including description of potential severity |  | Groups exposed & evidence of previous harm | Existing controls in place? |  | H/M/L | ACTION - Person responsible, date for achievement | Review action & date |
| 12 | Food | Poisoning, hot oils burns, bottled gas fire/explosion, trips/slips/ falls, crowd congestion | H 3 | All groups* - no known previous incident | Environmental Food Agency testing by District Council, H&S regs compliance including Food Hygiene Certs, trips/crowd, etc as in 1 & 7 above; LPG bottles checked for secure fastening , Event Marshal to monitor H&S compliance; Security of gas canisters and location to be checked and recorded | L 1 | L 3 | District Council to monitor food stalls; CD First Responders to provide First Aid during the main event and XXX (First Aider) on set-up day |  |
| 13 | Oil, diesel oil, hydraulic oil | Spills, slipping, pollution | H 3 | All groups* - no known previous incident | Event Marshal in possession of dry clean kiln-dried sand Event Marshal to monitor pathways & pedestrian areas | L 1 | L 3 |  |  |
| 14 | Liquified petroleum gas (LPG) | Fire, explosion, crushing due to crowd panic. Potential for serious harm | H 3 | All groups* – no previous incident | All bottles secured to prevent potential harm; waste litter regularly removed by Event Marshal, Managers and Named Stewards | L 1 | L 2 | Stewards to check on bottle containment and situation of waste build-up |  |
| 15 | Fire hydrants | Access prevention in the event of a fire hazard | L 2 | All groups* - no known previous incident | Hydrants painted yellow by Event Marshal for high visibility. Max length of fire hose 50m. | L 1 | L 2 | Event Marshal & Officials to prevent & ensure no parking on top of hydrants |  |
| 16 | Disorder | Alcohol. Spontaneous / pre-arranged violence between groups of youths | M 3 | All groups* | Police presence at all times; CD First Responders and G Thomas (First Aider) in attendance during Wakes operation. Mobile communications in place | L 3 | L 3 | Stewards / Police to patrol. Event Marshal & stewards to report signs of tension or conflict & liaise with Police. CD First Responders to provide First Aid during the main event and G Thomas (First Aider) on set-up day & emergency injury |  |

| WORK ACTIVITY |  | HAZARD | H/M/L | LIKELIHOOD |  | H/M/L | RISK | FURTHER ACTION REQUIRED |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Description of task | (including description of potential severity |  | Groups exposed & evidence of previous harm | Existing controls in place? |  | H/M/L | ACTION - Person responsible, date for achievement | Review action & date |
| 17 | Lost children | Large crowds | L 3 | All groups* - no previous incident | Staff Briefing Pack Appx D see ‘Lost Children’ procedure; mobile communications in place; meeting point for lost children | L 1 | L 1 | Male & female steward to accompany child to Event Control meeting point and follow lost child procedure |  |
| 18 | Pedestrian movement, during set-up especially children / young people | Children / young people on the streets during set-up afternoon | M/H | All groups* - no previous incident Especially the children / young people | Event Marshal/ Stewards/ Event Management to closely monitor/move on to ensure no pedestrian / vehicle conflict | M/H | M/H |  |  |
| 19 | Portable Toilets | Slip, trips and falls Chemical contamination Risk of unit being overturned vandalism | H 3 | All groups* | Toilets cleaned by PC Staff / Stewards sited on Clapgun Street car park. Sign posted. Paths lit by car park lights. Toilets lit by battery lights. | L 1 | L 3 | Event Marshal Event Marshal/ Stewards/ Event Management to monitor and check |  |

* All groups = Public, Stewards, Showmen